## Sheet1
|  | Start Date | 25.09.2023
Sr No. | Activity | Duration(days) | Possible end Date
1 | Admin Functionality - Backend | 5 | 30.09.2023
2 | Admin Functionality - Frontend | 3 | 03.09.2023
3 | API Interpretation | 2 | 05.09.2023
4 | API Integration - Frontend/Backend | 8 | 13.09.2023
5 | Deployment onto a cloud Instance | 4 | 17.09.2023
This is an approximate - based on the complexity of the response from the API.